## BOM_Error_Data
Date | Unit_ID | Error_Type | Stage_Detected | Department_Origin | Time_to_Resolve_Hours | Rework_Required | Estimated_Impact_Cost_USD
2025-01-27 | WT071003 | Incorrect Metadata | Pre-Release Review | Manufacturing | 1.8 | No | 0
2025-04-29 | WT071050 | Wrong Revision | Manufacturing Review | Manufacturing | 1.07 | Yes | 4049.59
2025-01-18 | WT071004 | Hierarchy Issue | SAP Load | Procurement | 4.35 | No | 0
2025-03-07 | WT071071 | Wrong Revision | SAP Load | Engineering | 2.56 | Yes | 1747.02
2025-05-04 | WT071001 | Wrong Revision | Manufacturing Review | Manufacturing | 2.27 | No | 0
2025-03-19 | WT071069 | Hierarchy Issue | SAP Load | Procurement | 4.14 | Yes | 4282.65
2025-06-29 | WT071011 | Duplicate Part | Pre-Release Review | Procurement | 0.71 | No | 0
2025-05-24 | WT071069 | Wrong Revision | SAP Load | Procurement | 5.05 | Yes | 819.44
2025-03-13 | WT071019 | Missing Part | SAP Load | Procurement | 5.64 | No | 0
2025-04-26 | WT071077 | Incorrect Metadata | SAP Load | Manufacturing | 5.36 | No | 0
2025-04-11 | WT071081 | Hierarchy Issue | SAP Load | Engineering | 3.54 | No | 0
2025-05-29 | WT071087 | Wrong Revision | Manufacturing Review | Procurement | 5.74 | No | 0
2025-05-06 | WT071031 | Incorrect Metadata | Manufacturing Review | Engineering | 1.45 | Yes | 2590.3
2025-01-16 | WT071048 | Wrong Revision | SAP Load | Manufacturing | 1.67 | Yes | 1861.08
2025-06-05 | WT071005 | Incorrect Metadata | Pre-Release Review | Manufacturing | 0.92 | No | 0
2025-06-20 | WT071072 | Hierarchy Issue | Manufacturing Review | Manufacturing | 2.65 | No | 0
2025-01-06 | WT071069 | Wrong Revision | SAP Load | Manufacturing | 2.53 | No | 0
2025-06-30 | WT071061 | Wrong Revision | SAP Load | Manufacturing | 2.45 | No | 0
2025-06-26 | WT071061 | Wrong Revision | Pre-Release Review | Procurement | 3.09 | No | 0
2025-06-12 | WT071003 | Wrong Revision | Manufacturing Review | Engineering | 2.14 | Yes | 3673.85
2025-01-15 | WT071037 | Hierarchy Issue | Pre-Release Review | Manufacturing | 1.74 | No | 0
2025-06-25 | WT071079 | Duplicate Part | SAP Load | Manufacturing | 5.15 | Yes | 761.32
2025-05-18 | WT071055 | Wrong Revision | Manufacturing Review | Procurement | 2.95 | Yes | 3856.74
2025-03-15 | WT071070 | Incorrect Metadata | Pre-Release Review | Engineering | 5.32 | Yes | 3208.81
2025-03-22 | WT071043 | Missing Part | Pre-Release Review | Procurement | 4.93 | Yes | 772.76
2025-01-29 | WT071069 | Missing Part | SAP Load | Engineering | 3.35 | No | 0
2025-03-27 | WT071004 | Incorrect Metadata | SAP Load | Engineering | 2.65 | Yes | 1149.59
2025-06-02 | WT071078 | Wrong Revision | SAP Load | Procurement | 2.09 | Yes | 1658.25
2025-01-20 | WT071079 | Wrong Revision | Pre-Release Review | Manufacturing | 1.42 | No | 0
2025-01-02 | WT071040 | Hierarchy Issue | Pre-Release Review | Procurement | 5.71 | Yes | 4302.36
2025-02-08 | WT071054 | Wrong Revision | Pre-Release Review | Engineering | 1.79 | Yes | 604.56
2025-03-23 | WT071039 | Duplicate Part | SAP Load | Engineering | 3.2 | Yes | 651.82
2025-06-14 | WT071033 | Wrong Revision | SAP Load | Manufacturing | 0.69 | No | 0
2025-02-08 | WT071066 | Missing Part | Manufacturing Review | Engineering | 5.83 | Yes | 912.18
2025-01-18 | WT071026 | Incorrect Metadata | Manufacturing Review | Engineering | 3.67 | No | 0
2025-03-13 | WT071049 | Hierarchy Issue | Manufacturing Review | Engineering | 1.84 | Yes | 3051.86
2025-03-21 | WT071047 | Wrong Revision | Pre-Release Review | Manufacturing | 2.76 | Yes | 3641.01
2025-04-01 | WT071019 | Wrong Revision | Manufacturing Review | Procurement | 1.09 | No | 0
2025-01-20 | WT071022 | Missing Part | SAP Load | Procurement | 1.83 | No | 0
2025-03-18 | WT071077 | Missing Part | Manufacturing Review | Engineering | 2.87 | No | 0
2025-05-31 | WT071085 | Hierarchy Issue | Pre-Release Review | Engineering | 3.03 | Yes | 4112.18
2025-01-07 | WT071099 | Hierarchy Issue | Pre-Release Review | Manufacturing | 0.98 | No | 0
2025-06-23 | WT071079 | Wrong Revision | SAP Load | Engineering | 2.91 | Yes | 445.91
2025-05-29 | WT071077 | Missing Part | Pre-Release Review | Procurement | 1.95 | No | 0
2025-05-22 | WT071090 | Hierarchy Issue | Pre-Release Review | Manufacturing | 2.05 | Yes | 2686.49
2025-03-07 | WT071027 | Wrong Revision | SAP Load | Procurement | 5.65 | Yes | 3015.02
2025-03-05 | WT071029 | Duplicate Part | Pre-Release Review | Engineering | 1.7 | No | 0
2025-06-21 | WT071092 | Incorrect Metadata | Pre-Release Review | Manufacturing | 1.36 | Yes | 766.83
2025-01-04 | WT071070 | Hierarchy Issue | Manufacturing Review | Engineering | 3.34 | Yes | 740.69
2025-02-24 | WT071096 | Hierarchy Issue | Pre-Release Review | Manufacturing | 2.01 | Yes | 2592.83
2025-04-24 | WT071019 | Duplicate Part | Manufacturing Review | Manufacturing | 4.02 | Yes | 3198.98
2025-03-25 | WT071032 | Duplicate Part | Manufacturing Review | Procurement | 3.9 | No | 0
2025-04-06 | WT071076 | Duplicate Part | Manufacturing Review | Engineering | 1.74 | No | 0
2025-05-17 | WT071012 | Duplicate Part | Manufacturing Review | Procurement | 5.5 | Yes | 4182.85
2025-04-09 | WT071081 | Duplicate Part | Manufacturing Review | Procurement | 5.34 | No | 0
2025-03-03 | WT071069 | Incorrect Metadata | SAP Load | Manufacturing | 1.29 | Yes | 3762.06
2025-04-10 | WT071006 | Duplicate Part | Pre-Release Review | Manufacturing | 5.41 | No | 0
2025-05-10 | WT071000 | Incorrect Metadata | Manufacturing Review | Manufacturing | 2.72 | Yes | 3680.19
2025-01-09 | WT071075 | Missing Part | SAP Load | Manufacturing | 3.8 | No | 0
2025-05-27 | WT071039 | Duplicate Part | Pre-Release Review | Engineering | 1.32 | Yes | 1724.54
2025-05-27 | WT071019 | Incorrect Metadata | Pre-Release Review | Procurement | 4.27 | Yes | 3937.23
2025-04-01 | WT071070 | Hierarchy Issue | SAP Load | Engineering | 2.59 | Yes | 3990.73
2025-03-02 | WT071023 | Duplicate Part | Pre-Release Review | Procurement | 4.35 | Yes | 2625.89
2025-06-02 | WT071093 | Missing Part | Manufacturing Review | Engineering | 4.68 | No | 0
2025-06-11 | WT071017 | Missing Part | SAP Load | Engineering | 3.17 | Yes | 4499.3
2025-03-27 | WT071028 | Incorrect Metadata | Pre-Release Review | Procurement | 2.22 | No | 0
2025-03-12 | WT071013 | Incorrect Metadata | Manufacturing Review | Engineering | 4.62 | No | 0
2025-05-24 | WT071005 | Incorrect Metadata | Pre-Release Review | Procurement | 3.82 | Yes | 3760.08
2025-01-17 | WT071043 | Missing Part | Pre-Release Review | Manufacturing | 0.52 | Yes | 1783.78
2025-05-28 | WT071011 | Duplicate Part | Manufacturing Review | Engineering | 1.78 | No | 0
2025-03-14 | WT071013 | Missing Part | Pre-Release Review | Manufacturing | 3.75 | No | 0
2025-05-15 | WT071030 | Missing Part | Manufacturing Review | Engineering | 1.84 | Yes | 2648.92
2025-01-07 | WT071019 | Incorrect Metadata | Pre-Release Review | Manufacturing | 2.18 | No | 0
2025-05-26 | WT071049 | Missing Part | Pre-Release Review | Engineering | 3.39 | No | 0
2025-01-02 | WT071025 | Missing Part | Manufacturing Review | Engineering | 5.59 | No | 0
2025-05-17 | WT071039 | Wrong Revision | SAP Load | Manufacturing | 3.81 | No | 0
2025-05-18 | WT071073 | Wrong Revision | SAP Load | Engineering | 1.16 | No | 0
2025-03-20 | WT071054 | Hierarchy Issue | SAP Load | Engineering | 5.15 | No | 0
2025-04-12 | WT071007 | Hierarchy Issue | Pre-Release Review | Manufacturing | 4.34 | No | 0
2025-05-21 | WT071050 | Wrong Revision | Manufacturing Review | Procurement | 2.39 | No | 0
2025-03-19 | WT071071 | Wrong Revision | Pre-Release Review | Procurement | 1.29 | No | 0
2025-02-13 | WT071001 | Missing Part | Manufacturing Review | Engineering | 2.8 | Yes | 3713.83
2025-03-11 | WT071085 | Incorrect Metadata | Pre-Release Review | Manufacturing | 0.79 | Yes | 1354.01
2025-01-15 | WT071089 | Hierarchy Issue | SAP Load | Engineering | 4.32 | No | 0
2025-05-03 | WT071059 | Duplicate Part | SAP Load | Procurement | 1.25 | Yes | 2734.35
2025-03-09 | WT071093 | Missing Part | Manufacturing Review | Engineering | 2.63 | Yes | 3400.28
2025-06-16 | WT071074 | Hierarchy Issue | Pre-Release Review | Manufacturing | 3.2 | No | 0
2025-02-02 | WT071026 | Duplicate Part | Pre-Release Review | Manufacturing | 2.2 | Yes | 2170.04
2025-02-25 | WT071090 | Wrong Revision | Pre-Release Review | Engineering | 2.76 | Yes | 2743.33
2025-02-08 | WT071082 | Wrong Revision | Pre-Release Review | Engineering | 0.55 | Yes | 3442.75
2025-04-19 | WT071059 | Incorrect Metadata | Pre-Release Review | Procurement | 1.94 | No | 0
2025-03-26 | WT071099 | Duplicate Part | SAP Load | Engineering | 4.44 | Yes | 4011.81
2025-03-31 | WT071040 | Hierarchy Issue | Manufacturing Review | Engineering | 0.86 | No | 0
2025-01-25 | WT071040 | Hierarchy Issue | Pre-Release Review | Manufacturing | 0.6 | Yes | 4450.59
2025-01-03 | WT071015 | Duplicate Part | SAP Load | Manufacturing | 5.44 | No | 0
2025-03-06 | WT071051 | Duplicate Part | Manufacturing Review | Procurement | 5.32 | No | 0
2025-02-23 | WT071082 | Wrong Revision | Manufacturing Review | Manufacturing | 4.03 | No | 0
2025-03-19 | WT071010 | Duplicate Part | Pre-Release Review | Manufacturing | 3.9 | Yes | 2435.43
2025-02-05 | WT071023 | Incorrect Metadata | SAP Load | Procurement | 3.31 | Yes | 3104.33
2025-03-12 | WT071056 | Incorrect Metadata | SAP Load | Procurement | 4.78 | Yes | 1494.04
2025-03-17 | WT071032 | Duplicate Part | Pre-Release Review | Manufacturing | 1.49 | Yes | 2892.83
2025-01-03 | WT071072 | Incorrect Metadata | SAP Load | Manufacturing | 0.72 | Yes | 1833.22
2025-01-08 | WT071055 | Incorrect Metadata | Pre-Release Review | Procurement | 5.02 | Yes | 3838.29
2025-05-24 | WT071012 | Incorrect Metadata | Pre-Release Review | Engineering | 2.2 | No | 0
2025-03-31 | WT071035 | Duplicate Part | SAP Load | Manufacturing | 4.47 | Yes | 163.15
2025-06-27 | WT071093 | Wrong Revision | Manufacturing Review | Procurement | 3.32 | No | 0
2025-02-28 | WT071074 | Wrong Revision | SAP Load | Manufacturing | 5.89 | No | 0
2025-05-29 | WT071044 | Hierarchy Issue | Pre-Release Review | Manufacturing | 0.73 | Yes | 1785.97
2025-03-18 | WT071092 | Hierarchy Issue | SAP Load | Manufacturing | 1.47 | No | 0
2025-02-06 | WT071068 | Wrong Revision | Manufacturing Review | Manufacturing | 3.62 | Yes | 2555.77
2025-05-15 | WT071056 | Incorrect Metadata | Pre-Release Review | Procurement | 5.5 | Yes | 4245.95
2025-06-14 | WT071078 | Hierarchy Issue | SAP Load | Engineering | 4.43 | No | 0
2025-03-28 | WT071024 | Incorrect Metadata | Manufacturing Review | Procurement | 3.79 | No | 0
2025-04-11 | WT071084 | Incorrect Metadata | Pre-Release Review | Manufacturing | 5.77 | No | 0
2025-02-16 | WT071079 | Wrong Revision | Pre-Release Review | Engineering | 5.12 | No | 0
2025-03-06 | WT071014 | Duplicate Part | SAP Load | Procurement | 4.63 | Yes | 1555.14
2025-02-28 | WT071093 | Hierarchy Issue | Pre-Release Review | Engineering | 0.56 | Yes | 1105.89
2025-01-21 | WT071028 | Missing Part | Pre-Release Review | Engineering | 5.39 | Yes | 3846.76
2025-03-28 | WT071028 | Missing Part | SAP Load | Engineering | 1.2 | Yes | 4124.95
2025-01-07 | WT071022 | Duplicate Part | SAP Load | Procurement | 3.6 | Yes | 3482.98

## Revision_Change_Log
Date | Unit_ID | Part_Number | Old_Revision | New_Revision | Change_Reason | Rework_Required
2025-04-06 | WT071157 | PN-10902 | A | C | Design Update | No
2025-02-08 | WT071146 | PN-18070 | C | C | Design Update | No
2025-06-18 | WT071159 | PN-14618 | A | D | Vendor Change | No
2025-01-08 | WT071116 | PN-11239 | C | D | Error Correction | No
2025-05-02 | WT071144 | PN-10227 | B | C | Error Correction | Yes
2025-04-20 | WT071146 | PN-15713 | C | B | Vendor Change | No
2025-02-28 | WT071106 | PN-12940 | C | C | Vendor Change | Yes
2025-03-07 | WT071172 | PN-16151 | C | B | Error Correction | Yes
2025-04-18 | WT071169 | PN-10374 | A | C | Vendor Change | Yes
2025-06-01 | WT071194 | PN-16834 | A | C | Error Correction | Yes
2025-03-07 | WT071180 | PN-13391 | C | D | Design Update | Yes
2025-03-04 | WT071102 | PN-12357 | C | B | Standardization | No
2025-01-07 | WT071117 | PN-10235 | C | B | Standardization | No
2025-06-25 | WT071131 | PN-15802 | B | C | Vendor Change | Yes
2025-05-08 | WT071151 | PN-16255 | C | B | Standardization | Yes
2025-02-26 | WT071167 | PN-18880 | B | B | Error Correction | No
2025-01-05 | WT071139 | PN-14330 | C | B | Design Update | No
2025-01-17 | WT071119 | PN-13717 | C | D | Standardization | No
2025-02-07 | WT071126 | PN-17941 | A | D | Error Correction | Yes
2025-02-12 | WT071120 | PN-18034 | C | C | Design Update | No
2025-02-04 | WT071165 | PN-17261 | C | D | Design Update | No
2025-03-06 | WT071146 | PN-18368 | B | D | Error Correction | Yes
2025-04-25 | WT071139 | PN-14113 | B | C | Error Correction | No
2025-01-09 | WT071193 | PN-10308 | C | D | Design Update | No
2025-02-04 | WT071177 | PN-17416 | B | D | Design Update | Yes
2025-02-28 | WT071165 | PN-17465 | B | B | Vendor Change | No
2025-02-13 | WT071190 | PN-13205 | C | D | Design Update | Yes
2025-06-30 | WT071148 | PN-14771 | B | B | Error Correction | Yes
2025-06-29 | WT071161 | PN-11879 | C | C | Design Update | No
2025-04-30 | WT071152 | PN-11119 | C | D | Standardization | No
2025-01-21 | WT071119 | PN-10407 | B | C | Vendor Change | Yes
2025-01-08 | WT071127 | PN-10519 | A | C | Error Correction | No
2025-02-19 | WT071136 | PN-15298 | A | C | Vendor Change | No
2025-04-12 | WT071152 | PN-19771 | A | C | Vendor Change | No
2025-03-25 | WT071185 | PN-18697 | B | D | Error Correction | No
2025-01-13 | WT071198 | PN-14421 | B | D | Standardization | Yes
2025-05-17 | WT071167 | PN-18080 | A | D | Error Correction | Yes
2025-01-08 | WT071175 | PN-11688 | C | C | Design Update | Yes
2025-06-02 | WT071163 | PN-15016 | B | D | Design Update | No
2025-06-12 | WT071105 | PN-17635 | B | D | Design Update | Yes
2025-02-06 | WT071165 | PN-16680 | B | C | Standardization | Yes
2025-02-11 | WT071106 | PN-19177 | A | B | Vendor Change | No
2025-05-08 | WT071106 | PN-15125 | B | B | Vendor Change | Yes
2025-05-11 | WT071176 | PN-13871 | C | C | Design Update | Yes
2025-06-25 | WT071176 | PN-17504 | C | D | Vendor Change | Yes
2025-05-19 | WT071111 | PN-16148 | B | D | Design Update | No
2025-04-17 | WT071108 | PN-15216 | B | B | Standardization | Yes
2025-06-07 | WT071173 | PN-16988 | A | B | Design Update | No
2025-02-05 | WT071171 | PN-18810 | B | D | Error Correction | Yes
2025-05-27 | WT071192 | PN-17927 | B | B | Error Correction | Yes
2025-01-23 | WT071143 | PN-17402 | B | C | Design Update | Yes
2025-05-09 | WT071122 | PN-11431 | B | C | Design Update | Yes
2025-04-26 | WT071145 | PN-17295 | B | D | Standardization | Yes
2025-04-13 | WT071102 | PN-18030 | A | C | Error Correction | No
2025-01-19 | WT071192 | PN-14834 | B | D | Standardization | No
2025-01-08 | WT071113 | PN-18415 | A | B | Design Update | No
2025-05-29 | WT071111 | PN-10084 | C | D | Vendor Change | No
2025-06-07 | WT071103 | PN-14321 | B | B | Error Correction | No
2025-03-15 | WT071109 | PN-13521 | C | C | Error Correction | Yes
2025-04-17 | WT071173 | PN-12501 | C | B | Error Correction | Yes
2025-03-17 | WT071194 | PN-18454 | B | D | Vendor Change | No
2025-05-14 | WT071124 | PN-13390 | A | B | Vendor Change | Yes
2025-02-22 | WT071105 | PN-12542 | B | D | Design Update | No
2025-01-22 | WT071120 | PN-13888 | A | C | Error Correction | Yes
2025-01-25 | WT071119 | PN-19119 | B | B | Vendor Change | No
2025-03-12 | WT071138 | PN-18810 | C | B | Error Correction | No
2025-05-23 | WT071138 | PN-15551 | B | D | Design Update | No
2025-03-29 | WT071137 | PN-16591 | C | C | Standardization | Yes
2025-01-22 | WT071164 | PN-18149 | B | C | Standardization | Yes
2025-06-11 | WT071156 | PN-19954 | B | D | Error Correction | Yes
2025-02-12 | WT071165 | PN-18872 | C | D | Design Update | Yes
2025-02-16 | WT071114 | PN-13161 | A | D | Error Correction | Yes
2025-04-28 | WT071159 | PN-11192 | B | B | Error Correction | No
2025-04-14 | WT071182 | PN-14850 | B | C | Error Correction | Yes
2025-06-22 | WT071104 | PN-14994 | B | C | Vendor Change | Yes
2025-02-16 | WT071137 | PN-14313 | C | C | Standardization | Yes
2025-05-14 | WT071197 | PN-11283 | C | C | Error Correction | No
2025-01-06 | WT071169 | PN-16320 | A | D | Vendor Change | Yes
2025-01-19 | WT071113 | PN-13259 | B | C | Error Correction | Yes
2025-03-25 | WT071143 | PN-13761 | C | B | Standardization | Yes
2025-03-15 | WT071135 | PN-17331 | C | B | Vendor Change | Yes
2025-01-20 | WT071105 | PN-15508 | A | B | Standardization | Yes
2025-02-13 | WT071125 | PN-11760 | B | B | Vendor Change | No
2025-04-04 | WT071144 | PN-16824 | C | B | Design Update | No
2025-05-12 | WT071140 | PN-15333 | C | C | Standardization | Yes
2025-04-13 | WT071123 | PN-16345 | B | B | Design Update | Yes
2025-02-08 | WT071138 | PN-16817 | C | D | Error Correction | No
2025-06-24 | WT071153 | PN-11673 | A | C | Standardization | No
2025-02-23 | WT071148 | PN-19306 | B | B | Standardization | No
2025-06-08 | WT071111 | PN-13492 | A | C | Design Update | Yes
2025-01-01 | WT071134 | PN-12820 | C | D | Vendor Change | No
2025-04-27 | WT071173 | PN-14075 | B | D | Error Correction | Yes
2025-01-05 | WT071169 | PN-14715 | B | B | Design Update | No
2025-03-12 | WT071152 | PN-18939 | C | C | Vendor Change | Yes
2025-01-12 | WT071106 | PN-10337 | A | D | Vendor Change | Yes
2025-03-18 | WT071179 | PN-10445 | C | B | Vendor Change | Yes
2025-06-16 | WT071139 | PN-15687 | A | C | Design Update | No
2025-02-01 | WT071177 | PN-14949 | A | D | Design Update | No
2025-06-02 | WT071161 | PN-14736 | A | D | Standardization | No
2025-04-07 | WT071142 | PN-16200 | A | D | Standardization | Yes

## KPI_Summary
Metric | Value
Total BOM Errors | 120
Rework Rate (%) | 51.67
Average Resolution Time (hrs) | 3.09
Total Estimated Cost Impact ($) | 164235.38

## Pivot_Error_Type
Error_Type | Error_Count
Duplicate Part | 23
Hierarchy Issue | 23
Incorrect Metadata | 25
Missing Part | 19
Wrong Revision | 30

## Pivot_Stage
Stage_Detected | Error_Count
Manufacturing Review | 33
Pre-Release Review | 47
SAP Load | 40

## Pivot_Monthly_Trend
Month | Error_Count
2025-01 | 23
2025-02 | 13
2025-03 | 33
2025-04 | 12
2025-05 | 23
2025-06 | 16

## Calc_Tables
KPI Summary (formula-driven)
Total BOM Errors | 120
Rework Rate (%) | 51.6667
Average Resolution Time (hrs) | 3.0915
Total Estimated Cost Impact ($) | 164235.38
Errors by Type
Error_Type | Count |  | Stage_Detected | Count
Duplicate Part | 23 |  | Manufacturing Review | 33
Hierarchy Issue | 23 |  | Pre-Release Review | 47
Incorrect Metadata | 25 |  | SAP Load | 40
Missing Part | 19
Wrong Revision | 30
Monthly Error Trend
Month | Start | End | Error_Count
Jan 2025 | 2025-01-01 | 2025-02-01 | 23
Feb 2025 | 2025-02-01 | 2025-03-01 | 13
Mar 2025 | 2025-03-01 | 2025-04-01 | 33
Apr 2025 | 2025-04-01 | 2025-05-01 | 12
May 2025 | 2025-05-01 | 2025-06-01 | 23
Jun 2025 | 2025-06-01 | 2025-07-01 | 16

## Dashboard
Engineering ERP Data Validation Dashboard (Simulated)
KPI | Value | Insights (auto)
Total BOM Errors | 120 | Top Error Type: | Wrong Revision
Rework Rate (%) | 51.6667 | Top Detection Stage: | Pre-Release Review
Average Resolution Time (hrs) | 3.0915 | Rework %: | 51.6667
Total Estimated Cost Impact ($) | 164235.38